## R&D
S.no | CV Code | Quantity | Team Lead | PO Date | PO Dispatch Date | On Time | Remarks
1 | A11CF | 1 kg | Leader A | 2026-06-01 | 2026-08-04 | NO | COA for 1 KG has been shared. 2 g of each sample sent to customer. Waiting for feedback. 10 g of compound was shipped
2 | B4I90 | 20 g | Leader A | 2026-05-09 | 2026-06-28 | NO | 20 g was shipped on 27/08/26. 25 g on hand
3 | A1TRP | 20 g | Leader B | 2026-05-09 | 2026-06-28 | NO | 20 g was shipped on 27/08/26. 25 g on hand
4 | B0MI2 | 20 g | Leader B | 2026-05-09 | 2026-06-28 | NO | 20 g was shipped on 27/08/26. 25 g on hand
5 | CK05R | 200 g | Leader A | 2026-04-01 | 2026-09-02 | YES | Started work on new scheme. Final compound was confirmed.
6 | A2NSQ | 200 g | Leader B | 2026-04-01 | 2026-09-02 | YES | Tweaking final stage to improve yields
7 | BG7JD | 500 g | Leader A | 2026-08-28 | 2026-10-30 | YES | Raw materials have been ordered

## Production
S.no | Project Code | Old/New | CAS no | Quantity (kgs) | Team Lead | PO Date | PO Dispatch Date | Disptach date | Reason for Delay
1 | A1F | Old | AAAB-AA-B | 100 | A | 2026-01-01 | 2026-01-21 | 2026-02-01 | Raw Materials Late
2 | 23D | Old | CCC-DD-A | 110 | B | 2026-01-02 | 2026-01-22 | 2026-02-02 | Reactor Availability
3 | M42 | Old | ABA-CA-B | 120 | B | 2026-01-03 | 2026-01-23 | 2026-02-03 | Shipping Delay
4 | A8T | Old | BBCA-AB-C | 130 | A | 2026-01-04 | 2026-01-24
5 | R5W | Old | CBA-CC-A | 140 | A | 2026-01-05 | 2026-01-25
6 | 9XQ | Old | BCBA-CB-C | 150 | A | 2026-01-06 | 2026-01-26
7 | 76V | Old | CDAB-BD-C | 160 | B | 2026-01-07 | 2026-01-27
8 | C2P | Old | DABB-DD-D | 170 | B | 2026-01-08 | 2026-01-28
9 | 4KB | Old | CDDB-DA-B | 180 | A | 2026-01-09 | 2026-01-29 | 2026-02-04 | Shipping Delay
10 | 3GI | Old | DBAC-AC-C | 190 | A | 2026-01-10 | 2026-01-30