## R&D
S.no | CV Code | Quantity | Team Lead | PO Date | PO Dispatch Date | On Time | Remarks
1 | J2N93 | 100 g |  | 2026-05-05 | 2026-08-02 | YES | 200 g of stage 7 compound was attempted to convert to stage 8 using catalyst, reaction monitored by TLC, isolated 85.7 g crude with 86.4% purity by HPLC.
2 | G9B83 | 0.6 kg | Leader A | 2026-03-07 | 2026-04-28 | YES | Scale-up trial for stage 2 completed at 1000 g scale; 42% yield, within spec. Analytical method development for the final compound is complete; validation batch scheduled next week. COA for 100 g has been shared. 1 g of sample sent to customer, waiting for feedback.
3 | L5Q46 | 10 g | Leader A | 2026-03-15 | 2026-07-04 | YES | 100 g of stage 6 compound converted to stage 7 and got 835.0 g with 93.9% purity by HPLC (88% yields). Analytical method development for the final compound is complete; validation batch scheduled next week. 50 g of stage 8 compound was attempted to convert to stage 9 using catalyst, reaction monitored by TLC, isolated 860.5 g crude with 98.2% purity by HPLC. Scale-up trial for stage 3 completed at 1000 g scale; 66% yield, within spec.
4 | K6R20 | 100 g | Leader D | 2026-05-22 | 2026-08-15 | YES | Analytical method development for the final compound is complete; validation batch scheduled next week. Tweaking the final stage to improve yields; current best is 87.2% purity by HPLC. 10 g was shipped on 11/08/26, ~60 g is in hand.
5 | K6N60 | 1 g | Leader D | 2026-03-26 | 2026-06-05 | YES | 1000 g of stage 1 compound was attempted to convert to stage 2 using catalyst, reaction monitored by TLC, isolated 183.2 g crude with 86.5% purity by HPLC.
6 | G9N29 | 200 g | Leader C | 2026-03-04 | 2026-04-02 | NO | 5 g of crude product purified by column chromatography, got 900.1 g with 96.0% purity, confirmed by HNMR. Process safety review completed for stage 1; no blocking concerns raised. Started work on new scheme for this project; route confirmed with the technical team. 10 g of stage 6 compound was attempted to convert to stage 7 using catalyst, reaction monitored by TLC, isolated 428.1 g crude with 88.3% purity by HPLC.
7 | G3N39 | 1 g | Leader D | 2026-02-08 | 2026-06-04 | YES | 5 g of crude product purified by column chromatography, got 266.1 g with 88.4% purity, confirmed by HNMR. 500 g stability sample pulled for the 3-month timepoint; results pending. Raw materials have been ordered; reaction setup planned for next week.
8 | L6C30 | 20 g | Leader B | 2026-05-31 | 2026-09-26 | NO | Analytical method development for the final compound is complete; validation batch scheduled next week. Raw materials have been ordered; reaction setup planned for next week. COA for 750 g has been shared. 20 g of sample sent to customer, waiting for feedback. Scale-up trial for stage 3 completed at 2 g scale; 88% yield, within spec.
9 | K8E78 | 10 g | Leader E | 2026-08-18 | 2026-09-25 | NO | COA for 1000 g has been shared. 25 g of sample sent to customer, waiting for feedback. Process safety review completed for stage 9; no blocking concerns raised.
10 | D1Q81 | 0.7 kg |  | 2026-04-25 | 2026-07-27 | NO | 750 g stability sample pulled for the 3-month timepoint; results pending. Started work on new scheme for this project; route confirmed with the technical team.

## Production
S.no | Project Code | Old/New | CAS no | Quantity (kgs) | Team Lead | PO Date | PO Dispatch Date | Disptach date | Reason for Delay
1 | Y8L | Old | CBA-BA-B | 200 | B | 2026-06-04 | 2026-06-22 | 2026-06-27
2 | T7R | Old | DDA-BC-C | 250 | B | 2026-07-01 | 2026-07-25 |  | Shipping Delay
3 | S6Q | New | CBC-BD-A | 100 | A | 2026-04-22 | 2026-05-14 |  | Raw Materials Late
4 | W3P | New | BCC-BB-C | 25 | F | 2026-05-17 | 2026-06-13 | 2026-06-19
5 | S2J | Old | CAB-AA-D | 150 | E | 2026-05-04 | 2026-05-19 | 2026-05-24
6 | T3J | Old | ADC-CA-D | 400 | F | 2026-05-16 | 2026-06-07 |  | Reactor Availability
7 | W1A | Old | CCA-BD-A | 250 | F | 2026-08-05 | 2026-08-31 | 2026-09-06
8 | V4L | Old | DCC-BB-A | 75 | A | 2026-04-19 | 2026-05-11 |  | Reactor Availability
9 | T7K | Old | CAA-BA-C | 200 | E | 2026-06-22 | 2026-07-13 |  | Shipping Delay
10 | V6F | Old | BAB-CA-A | 50 | C | 2026-04-23 | 2026-05-11 |  | Reactor Availability
11 | Y1K | New | CAD-DA-D | 200 | F | 2026-08-05 | 2026-08-23
12 | U1P | Old | DDC-DA-B | 50 | A | 2026-04-11 | 2026-04-29 | 2026-05-02